## Content plan
| Project name: |  | ANNUAL REPORT 2025
Review /controlling
|  | Page | no. of pages | Responsibility | Status | Purpose | Description | Graphic | Link to file | Project team notes | Deadline | Ready for 1. review | Ready for proof reading
Define Project team |  | N/A | N/A | Eric, Project lead | DONE | transparent process | Ensure every task is accounted for and planned across the company | N/A | N/A |  | Whenever
Plan meeting schedule |  | N/A | N/A | Project team | DONE | transparent process | Help to set and reach deadlines | N/A | N/A
Kick-off meeting |  | N/A | N/A | Eric, Project lead | DONE | transparent process | Clarify theme, meeting schedule, messaging, storyline and content outline | N/A | N/A
Agree upon theme, key messages and storyline |  | N/A | N/A | Project team | In progress | transparent process
Create content outline |  | N/A | N/A | Project team | In progress | transparent process
1. round of edits |  | N/A | N/A |  |  | transparent process | Set a deadline for 1. drafts and documents like case studies, which can be made whenever. |  |  |  | Before year end
ANNUAL REPORT CONTENT [Inspiration - you can define your own content requirements, and then move them to the timeline as well]
Table of contents |  | 2 | 1 | Eric, project lead |  |  | Base it on content outline |  |  | 1. draft before year end. | Last
Case studies |  | 3, 5 | 1 | Cathrine, Marketing | On track |  |  |  |  | Finalize as soon as possible | Before year end
Introduction | [9 empty] | Is there anything from last year that can be re-used. | Before year end
Letter from Chairman & CEO | [9 empty] | Create a draft, in the beginning, helps to outline the tone of voice throughout the process. Minor adjustments can be made in the end. | Draft november/ december
Highlights | [9 empty] | Outline what highlights to include before year-end | After fiscal year-end
Key events | [9 empty] | Finalize as soon as possible | Before year end
Strategy (product, market review, outlook) | [9 empty] | Finalize as soon as possible | Before year end
Risk management | [6 empty] | E.g. Financial, currency, and interest |  |  | Is there anything from last year that can be re-used. Prepare 1. draft before year-end. | Finalize right before publication date
financial hightlights |  | 20 | 4 | Finance team | On track | Quick insights |  |  |  | Outline what highlights to include before year-end | after year-end
financial review | [9 empty] | You can prepare tone of voice as soon as you have an idea about the the numbers | after year-end
Environment, Social, and Governance | [9 empty] | Finalize as soon as possible | Before year end
Management, Board of Directors | [9 empty] | Finalize as soon as possible | finish asap
shareholder information | [9 empty] | Prepare layout | Prepare draft finalize after year-end
Consolidated financial statements + notes | [10 empty] | new year
Parent financial statements + notes | [10 empty] | new year
Statement board and directors | [9 empty] | Finalize as soon as possible
Independent auditors report
Company information | [9 empty] | Finalize as soon as possible | Before year end

## Timeline
Project start date: | 2025-09-26 | [5 empty] | 2025-10-20 | [8 empty] | 2025-12-22 | [8 empty] | 2026-02-09
|  | This date controls the timeline | [5 empty] | 2025-10-06 |  |  |  | 2025-11-03 |  |  |  | 2025-12-01 |  |  |  |  | 2026-01-05 |  |  |  | 2026-02-02 |  |  |  | 2026-03-02
Project name: | ANNUAL REPORT 2025 |  |  |  |  | Week starting | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16
Content [define your own] | Responsible | Start | End | Days | Status | Process
Define Project team | Project lead | 2025-09-26 | 2026-10-01 | 265 | Complete | 100%
Plan meeting schedule | Project lead | 2025-09-26 | 2025-10-01 | 4 | Complete | 100% | bar: 2025-09-29
Kick-off meeting | Complete project team | 2025-10-03 | 2025-10-03 | 1 | Complete | 100% | bar: 2025-09-29
Agree upon theme, key messages and storyline | Complete project team | 2025-10-03 | 2025-10-03 | 1 | Complete | 100% | bar: 2025-09-29
Create content outline | Complete project team | 2025-10-03 | 2025-10-24 | 16 | In progress | 75% | bar: 2025-10-20
1. round of edits | Review process team | 2025-12-05 | 2025-12-19 | 11 | Not started | 0% | bar: 2025-12-15
Table of contents | Project lead | 2025-10-03 | 2025-10-24 | 16 | Review | 100% | bar: 2025-10-20
Case studies | Marketing | 2025-09-26 | 2025-12-05 | 51 | Blocked | 25% | bar: 2025-12-01
Introduction | Project lead | 2025-11-12 | 2025-11-12 | 1 | Not started | 0% | bar: 2025-11-10
Letter from Chairman & CEO | Marketing, CEO, & Chairman | 2025-10-10 | 2025-10-24 | 11 | In progress | 45% | bar: 2025-10-20
Highlights | Project lead | 2025-11-12 | 2026-02-14 | 68 | Review | 90% | bar: 2026-02-09
Key events | CEO | 2025-11-12 | 2025-12-05 | 18 | Not started | 0% | bar: 2025-12-01
Strategy (product, market review, outlook) | CEO and Marketing | 2025-10-10 | 2025-12-05 | 41 | In progress | 65% | bar: 2025-12-01
Risk management | FInance | 2025-11-12 | 2026-02-14 | 68 | In progress | 85% | bar: 2026-02-09
financial hightlights | FInance | 2026-01-01 | 2026-02-14 | 32 | Not started | 0% | bar: 2026-02-09
financial review | FInance | 2026-01-01 | 2026-02-14 | 32 | Not started | 0% | bar: 2026-02-09
Environment, Social, and Governance | HR, finance, Marketing, CEO | 2026-10-24 | 2026-01-10 | -205 | Blocked | 80% | bar: 2026-01-05
Management, Board of Directors | Marketing | 2026-01-01 | 2026-02-14 | 32 | Not started | 0% | bar: 2026-02-09
shareholder information | Finance | 2026-01-01 | 2026-02-14 | 32 | Not started | 0% | bar: 2026-02-09
Consolidated financial statements + notes | Finance | 2026-01-01 | 2026-02-14 | 32 | Not started | 0% | bar: 2026-02-09
Parent financial statements + notes | Finance | 2026-01-01 | 2026-02-14 | 32 | Not started | 0% | bar: 2026-02-09
Statement board and directors | Board and marketing | 2025-11-12 | 2026-02-14 | 68 | Not started | 0% | bar: 2026-02-09
Independent auditors report | Audit firm | 2026-01-10 | 2025-01-26 | -250 | Not started | 0%
Company information | Marketing | 2025-10-17 | 2025-10-20 | 2 | Complete | 100% | bar: 2025-10-20
Publish date |  | 2026-03-13 | 2026-03-13 | 1 | Not started | 0% | bar: 2026-03-09
Status
Not started
In progress
Blocked
Review
Complete
Formulas:
Days = NETWORKDAYS([Start],[End])

## Project team and repsonsibiliti
Project team, roles and responsibilities, & review process
| Team | Person | Role | Responsibility
Internal | Finance | CFO | Project lead // decision-maker
| Finance | Finance Manager | Coordinator
| Directors | CEO | Decision-maker
| Board | Chairman | Influencer
| Marketing | marketing manager | content creator and editor
| Board | Board of directors | Final review
External | Agency | Layout
| PR | Content review
Other stakeholders | Audit firm | Auditor